As of 16 April, 2023

Government of the People's Republic of Bangladesh

Ministry of Labour and Employment

3rd Implementation Status of National Action Plan (NAP) on the Labour Sector of Bangladesh (2021-2026)

- During the 9th session of the EU-Bangladesh Joint Economic Commission held in October 2019, the Government agreed to develop a National Action Plan (NAP) on the Labour Sector of Bangladesh (2021–2026). The Action Plan was developed in consultation with the European Union (EU) and was shared with the EU on 1 July 2021.The NAP is a commitment of the Government of Bangladesh to uphold labour rights and workplace safety in the country. The NAP contains specific actions on legal and administrative reforms as well as enforcement of laws, capacity building and promotional activities. There will be a strong engagement of the tripartite constituents through its implementation process; and, where appropriate, the International Labour Organization (ILO) and other development partners will be engaged in implementing the specific actions of the NAP.

- The Ministry of Labour and Employment (MOLE) has formed a 'Tripartite Implementation and Monitoring Committee'(TIMC) by a circular dated 11 August 2021. The responsibilities of the TIMC include: (1) Monitor the progress of implementation of the time-bound actions contained in the National Action Plan (NAP), shared with the European Union (EU) as well as Roadmap shared with ILO; and (2) Provide overall directions for the implementation of both the documents. In the meantime, six meetings of the TIMC have been held so far. The last meeting was held on 16 April, 2023.

- NAP Actions and Progress Made

The 1st and 2nd updates on the implementation status of the NPA were published in the MOLE website on 13 April 2022 and on 23 October, 2022 respectively. The 3rd implementation status was discussion with the tripartite constituents in the TIMC meeting held on 16 April 2023 under the Chair of Secretary, Ministry of Labour and Employment (MOLE).

Action 1 Bring Bangladesh labour laws in compliance with ILO standards on freedom of association and collective bargaining

1.1 Amendment of the Bangladesh Labour Rules (BLR), 2015

- The amended Bangladesh Labour Rules, 2015 have been published through gazette notification on 1 September 2022. (S.R.O No.-284-Law/2022).

- The amendment process took into consideration the recommendations made by ILO Supervisory Bodies. Some of the pending recommendations require amendment of Bangladesh Labour Act which are expected to be considered following further amendment to the Bangladesh Labour Act, 2006 (see Action 1.3 below).

1.2 Amendment of the Bangladesh Labour Act, 2006 (as amended in 2018)

- Proposals for amendment of Bangladesh Labour Act have been received from 17 government and organizations of employers and workers.

- The Tripartite Working Group (TWG), formed for amending Bangladesh Labour Act 2006 is working the amendment proposals. By this time, 10 meetings of TWG have been organized with the last one held on 10 April 2023

- ILO has shared a Technical Note and Global Good Practices to align Bangladesh Labour Laws with Selected International Labour Standards.

- ILO is assisting the Tripartite Working Group through a series of workshops on how the Technical Note can be utilized as a tool to align Bangladesh labour laws with the observations of the Committee of Experts on the Application of Conventions and Recommendations. By this time, four workshops have been organized, with the last one held on 29 March 2023.

- Upon the conclusion of TWG’s work, the proposed amendments will be look into by Tripartite Labour Law Reform Committee (TLRC) towards further vetting by National Tripartite Consultative Council (NTCC).

- The BLA amendment process is expected to be completed by December, 2023.

1.3 Amendment of Bangladesh Labour Rules, 2015, after BLA amendment

- After the amendment of BLA in 2022, further new amendments to the Bangladesh Labour Rules will be considered through the tripartite mechanism.

1.4 Adoption of Export Processing Zone (EPZ) Labour Rules

- The Bangladesh EPZ Labour Rules, 2022 has been published in the Bangladesh Gazette on 4 October, 2022 (S.R.O No-295).

- During 22 February - 21 March, 2023 BEPZA has conducted Workshops cum Training sessions in all EPZs on “Proper implementation of the Bangladesh EPZ Labor Rules, 2022”.

1.5Amendment of Bangladesh EPZ Labour Act, 2019

- The work to amend the Bangladesh EPZ Labour Act, 2019 will be started in July 2023. A Tripartite Standing Committee will work on this and the whole exercise is expected to be completed by June 2025.

- The ILO has prepared a Technical Note and Global Good Practices to align Bangladesh Labour Laws with selected International Labour Standards. Stakeholder consultation workshops are being organized on the same. The representatives from BEPZA attended the workshops.

Action 2 Eliminate child labour in all its forms by 2025

Action2.1 Regulatory and policy framework for the elimination of child labour

Action2.1.1Ratification of ILO Convention 138

- Bangladesh has ratified the ILO Minimum Age Convention, 1973 (No. 138) on 22 March 2022.

    - Modification of the National Plan of Action to Eliminate Child Labour

- The modified National Plan of Action (NPA) to Eliminate Child Labour (2021-2025) was published on 12 December 2021. The document is being translated in Bangla.

2.1.3 Updating the List of Hazardous Jobs

- The list of hazardous work has been updated with five new sectors which are: (1) Work related to fish drying, (2) Street-based informal work, (3) Work related to production, collection and transportation of bricks or collection and transportation of stone, (4) Informal /local tailoring and clothe making (5) Garbage and waste management related work.

- The updated list of 43 sectors has been published through a Gazette Notification on 29 April, 2022.

2.2 Strengthen investigations and increase the number of convictions for child labour

2.2.1 Improve the labour inspectorate/other public authorities who investigate cases of child labour and ensure convictions

- To improve the labour inspection capacity the number of labour inspectors is being increased gradually which is provided in detail under Section 7.

- Special Yearly Plan of Action is being implemented since 2022 to eliminating child labour from Keraniganj area.

- As of January, 2023, for employing child labour 555 cases have been filed to the Labour Court. Of them 205 cases have been resolved.

- Regular training courses are being organized for the Labour inspectors by the DIFE. In 2021-22 Financial Year, 27 training courses and 7 workshops were arranged for the labour inspectors. In addition, 25 training courses organized by GIZ.

2.2.2	Cooperation with different public authorities

- There are National and Divisional Councils as well as District and Upazila level committees to streamline collective efforts to eliminate child labour. These councils and committees, comprising representatives from NGOs and CSOs, hold regular meetings to take account of and follow up on the progress achieved.

- As of 16 April, 2023, 11 meetings of National Child Labour Welfare Council (NCLWC), 68 meetings of Divisional Councils and 157 meeting of District Level Committees have been organized.

  - Projects on (hazardous) child labour/child labour survey

    - Implementation of a Government funded project

- Through implementation of the government funded project “Eradication of Hazardous Child Labour from Bangladesh (4th Phase)” 100 thousand children have been withdrawn from hazardous work.

- The project provided 6 months’ non-formal education and 4 months’ skill development training and monthly stipend of Taka 1000 for 10 months to each children through mobile banking system. Taka 13 thousand per child has been provided as seed money to setup small business.

2.3.2 Conduct a child labour survey by Bangladesh

With the support from ILO, the Bangladesh Bureau of Statistics (BBS) has conducted a Child Labour Survey. The report of the survey is at final stage.

    - Design and implement programmes of action

- The NPA to Eliminate Child Labour (2021-2025) has identified actions of different ministries and organizations for elimination of child labour.

- A Feasibility Study towards implementing a project on elimination of child labour from all sectors of the economy has been started.

2.3.4 Enhance Child Labour Unit of MOLE

- The Child Labour Unit of MOLE has been strengthened with additional manpower head by a Deputy Secretary along with required support staff.

2.4 Awareness raising action and process

- All actions are continuously are being implemented on regular basis.

- Every year, MOLE allocates financial resources from its revenue budget to Divisional and District level committees to organise meetings, seminars and workshops. This Financial Year (2022-2023) the MoLE has allocated 2.96 million BDT for the Committees.

- A workshop supported by UNICEF was held on 5th December, 2022.

Action 3 Combat violence against workers, harassment, unfair labour practices and anti-union discrimination

Action 3.1 Preventive measures

3.1.1 Conduct regular training for awareness raising for responsible factory security staff, police and employers to prevent violence, harassment, unfair labour practices and anti-union acts

DoL

- Regular training programmes are being implemented for awareness raising of factory security staff, management staff, and government officials through its four Industrial Relations Institutes (IRIs) and 32 Labour Welfare Centres (LWCs) to prevent violence, harassment, unfair labour practices and anti-union acts. From July 2020 to 31 March 2023, a number of 27,588 participants with nearly 42% attended these training programmes.

- On “Gender Equality and Elimination of Violence and Harassment in the workplace” a total of 10 batches of training have been conducted for 315 DoL employees throughout the country in November 2022.

- On “Gender sensitive facilitation skills” a residential training session for 25 DoL officials was organized during 10-13 March, 2023,

Industrial Police:

- During January 2021 to March 2023, the Industrial Police conducted 3,930 hours of training for its personnel. Among them, 2,088 were males and 182 females.

- All training courses included, among other issues, Labour Act, 2006, human rights, labour rights and other topics concerning industrial relations management.

BEPZA

- During June 2021 to March 2023, BEPZA has provided training to 5017 participants including Industrial Police, Security Personnel, Employers/Management and Workers.

- The ILO, Dhaka is supporting BEPZA in developing training modules. On 06 April 2023 the Country Office Dhaka has shared a concept note on training module on which a review/discussion meeting between ILO, Dhaka and BEPZA was held on 10 April 2023.

3.1.2 Develop and regularly update (online) databases to provide an overview of number and nature of training programmes as well as number of trainees among factory security staff, police, employers and workers

- Database for training related information has been developed and linked to DoL’s website. DoL has been working on upgradation of the database regarding training information in consultation with associated stakeholder and experts.

- The BEPZA is working to establish an online database with relevant information of the trainees (segregated by name, designation, factory/ WWA, age, sex etc.) and the same will be completed within the stipulated timeline 2023.

- A separate database is being maintained by Home Affairs and Ministry of Law.

3.1.3 Develop a compendium in Bangla language of all existing and relevant laws, rules and regulations (including the use of minimum force and applicable sanctions or penalties for any proven violation) in order to train and raise awareness among industrial police and relevant law enforcement agencies (LEAs)

- The Ministry of Home Affairs (MoHA) has entrusted the Industrial Policy authorities to carry out this task. By this time MoHA has drafted the compendium. It is at the final stage to be published.

3.1.4 Continue to train and provide clear instructions to the industrial police and relevant LEAs on the use of minimum force, respect of human rights and labour rights, including on trade union rights and civil liberties during labour protests

- Industrial Police are regularly being trained on the use of minimum force, respect of human rights and labour rights, including on trade union rights and civil liberties during labour protests at Industrial Relations Institutes (IRIs). Two batches of such training were organized in November 2022.

- Both DOL and DIFE are entrusted with monitoring the case proceedings and management, including for those concerning alleged acts of violence and harassment against workers.

Action 3.2 Investigation of violence and harassment against workers, anti-union discrimination and unfair labour practices

3.2.1 Continue to provide regular training and clear instructions (including monitoring of instructions) for all DOL staff handling complaints on how to comply with the SOPs on anti-union discrimination and unfair labour practices against workers

- Regular training and instructions are being provided to the DOL staff handling complaints related to anti-union discrimination and unfair labour practices against workers.

- On remediation of unfair labour practices/anti trade union discrimination a workshop has been conducted for the officials of DoL DIFE, BEPZA and Industrial Police Judiciary from Labour Courts and Labour Appellate Tribunals on 24 January, 2023.

3.2.2 Continue to provide regular information to all workers on their rights and to complain and access legal support in case those rights are violated/ abused

  - The workers are regularly being sensitized on their rights, submitting complaints and accessing legal support in case of any violated their right through trainings and workshop organized by DOL.

  - On remediation of unfair labour practices/anti trade union a workshop for workers’ representatives from IBC, NCCWE and National Sramik League has been organized on 24 January 2023.

- The Department of Inspection for Factories and Establishments (DIFE) labour inspectors are regularly conducting information sessions/motivational campaigns at factory level. From July, 2022 to March 2023 about 879 such sessions have been conducted at factory level.

3.2.3 Continue to sensitise managers/ employers, security staff on how they can support the investigations

- The managers and security personnel are regularly being sensitized on how they can support investigation of complaints through trainings and workshop organized by DOL.

3.2.4	Continue to provide regular training and clear instructions (including monitoring of instructions) for all personnel handling cases of alleged acts of violence and harassment against workers, including in cases of protests

- Regular training and instructions are being provided to the relevant personnel handling cases of alleged acts of violence and harassment against workers.

Action 3.3 Ensure timely and dissuasive sanctions/convictions and related information

3.3.1 Compile and regularly update statistics on complaints received and of alleged incidents of violence and harassment, their follow-up including remedies for victims and sanctions/convictions imposed

- The full record of proceedings of unfair labour practices and anti-union discrimination is maintained in the publicly accessible database managed by DOL.

- From 2013 to 31 March 2023, a total of 206 complaints on anti-union discrimination and unfair labour practices were submitted to DoL. Of all the complaints, 196 have been settled (183 complaints have been amicably disposed of, and 13 cases were filed in Labour Courts). Investigations are ongoing on the remaining 10 complaints.

Action 3.4 Promoting Social Dialogue

3.4.1 Developing institutional mechanism and capacity building for national and sectoral Tripartite Consultative Councils (TCCs)

- ILO is proving support to develop a roadmap on social partners’ awareness and capacity building for social dialogue and collective bargaining at all levels. The activities include training sessions, workshops, focus group discussions, information sessions etc.

- In June 2022, initial discussions were held with ILO-HQ for an assessment mission of social dialogue mechanisms/ institutions (SDI). Through this mission a work-plan has been developed by the constituents with recommendations to strengthen the practices of social dialogue after conducting a self-diagnosis engaging the self-assessment method for social dialogue institutions (SAM-SDI) tool/methodology developed by the International Labour Organization.

- From January 2022 to April 2023 six meetings of NTCC has been organized. During May 2021 to April 2023, six meetings of RMG TCC have also been organized.

Action 4 Increase the success rate of application for trade union registration (paper and online)

Action 4.1 Explore and implement ways of further simplifying the registration process through tripartite consultations

    - Overhaul the existing online Registration System

- The online trade union registration process has been fully functional since October 2022 (https://www.mygov.bd/).

- The user friendly versions of the relevant Forms have been linked with the online system.

- All trade union registration applications are being accepted and processed through online system.

4.1.2 Establish a pre-application service at the Department of Labour (DOL)

- The pre-application service desks are fully operational in submitting application through online if applicants desire so.

4.1.3 Continuing with the provision for offline registration system

- Currently no application is being accepted manually.

Action 4.2 Training workers and employers on Trade Union Registration Process

- Regular trainings are provided to workers, management staff and government officials by DOL through its four Industrial Relations Institutes (IRIs) and 32 Labour Welfare Centres (LWCs).

- On 23 January 2023, a workshop on online trade union registration process through myGOv platform was organized for the workers representatives from IBC, NCCWE and National Sramik League.

- During July 2020 to 31 March, 2023, the DOL has trained 27,588 workers, management staff, and government officials on trade union registration process, among other issues through 4 IRIs and 32 LWCs with nearly 42% of female participants.

Action4.3 Publicly accessible online database on registration to be made fully operational and regularly updated

- The Publicly Accessible Online Database (http://103.48.18.197/en) has been activated on 30 September 2021 and is being updated on regular basis.

Action 5 Eliminate the backlog of cases at labour courts, including in the Dhaka Metropolitan Area

5.1 Take steps to make the three newly established Labour Courts fully functional

- Following setting up offices, recruitment of Judges, and getting nominations of representatives from employers and workers, the three new Labour Courts established in Sylhet, Barishal, and Rangpur are now fully functional.

- Previously, 30 judges and 30 lawyers were trained on international labour standards at the International Training Centre of ILO in Turin, Italy.

- Training for court officials may be organized abroad as well, with the support of ILO and development partners.

5.2 Establishment of new labour courts in Narayanganj, Gazipur, Cumilla and Faridpur districts

- After setting up offices, deployment of office staffs and getting nominations of representatives from employers and workers the three new courts in Narayanjanj, Cumilla and Gazipur are functional now.

5.3 Deployment of one Additional Judge (Member) to the Labour Appellate Tribunal

- On 31 August 2022, MoPA sanctioned the post of an additional Judge (Member) for the Labour Appellate Tribunal, along with other support staff. Appointment against the posts will be made upon receipt of the Finance Division’s approval.

5.4 Establish pilot processes to classify cases in consultation with the Judges of the Labour Courts with a view to addressing case backlogs

- A workshop was organized on 13 August 2022 to discuss the issue of piloting the classification of cases in the Labour Courts. The workshop generated a number of recommendations which are being put into practice. Feedback from this exercise would feed into further concretizing the work of classification.

5.5 Independent conciliation and arbitration system as a means of Alternative Dispute Resolution (ADR)

5.5.1 Establish a Conciliation and Arbitration Cell at DOL to provide secretariat service and monitor individual cases as need be

- A three-member Conciliation and Arbitration Cell has been established at DoL on 29 September 2021. The Cell stands ready to extend secretariat service to the conciliators and the panel of arbitrators.

- During 2013 to 31 March 2023, a total of 114 conciliation applications have been submitted to the DoL. Of these, 106 industrial disputes have been settled through DoL’s conciliation mechanism, 05 industrial disputes have been ceased according to BLA, 2006 and only 03 conciliation applications remained under process.

5.5.2  Develop an SOP for conciliation system through tripartite consultations

- The SoP for Conciliation developed through tripartite consolation has been approved by NTCC at its 73rd meeting held on 2 February, 2023.

5.5.3 Appointment of conciliators through gazette notification

- Through a gazette notification 15 conciliators for 15 different jurisdiction of DOL have been appointed by the Ministry of Labour and Employment on 10 March, 2022 to settle industrial disputes.

    - Develop an SOP for arbitration system through tripartite consultations

- A workshop on industrial dispute settlement, focusing on developing an SoP for arbitration, was organized on 25 January 2023 with the representatives from workers, employers and government.

5.5.5 Establish an arbitrators’ panel

- The work on preparing guideline for appointment of independent arbitrators through tripartite Focused Group Discussion (FGD) is ongoing.

5.5.6 Promote conciliation and arbitration system as ADR

- On 25 October 2022, ILO facilitated a self-assessment Mission based on the LABOURLAW’s diagnostic tool, which accomplished the following activities:

- Assess the effectiveness of the dispute resolution mechanism/services.

- Identify gaps requiring attention.

- Develop the outline of an action plan aiming to improve the effective, functioning and impact of the dispute resolution mechanism/services.

- A tripartite workshop on industrial dispute settlement was organized on 26 October, 2022 to concretizing the findings of the self-assessment mission.

5.5.7 Provide information sessions on the conciliation and arbitration system to workers, employers and DOL officials

- A tripartite workshop on industrial dispute settlement focusing on conciliation and arbitration system was organized on 25 January 2023.

Action 6 Set up an efficient system to follow-up on worker’s complaints received through helpline

6.1 Continuation of the helpline (16357) under revenue budget of DIFE

- The helpline is operational under the revenue budget of DIFE since June 2020.

6.2 Establishment of a complaint management cell to follow up the cases directly by the labour inspectors

- A Complaint Management Cell has been established at DIFE on 21 December 2020.

6.3 Develop a database of the complaints covering relevant information

- A database of complaints received via the helpline has been developed in December 2021.

- During July 2022 to March 2023, a total of 3,479 complaints have been received. Of which 645 complaints were received through the online website, helpline and emails, while the remaining 2834 complaints were received through the conventional process. As of 31 March 2023 a total 3,348 were resolved. The rest are under process.

6.4 Organise regular training programme for all service personnel/officials receiving complaints via the helpline on SOP on grievance handling

- Regular trainings are being provided as per training need assessment.

6.5 Establishment of the Helpline for all workers in EPZs

- The 24/7 hours BEPZA Helpline 16128 has been inaugurated on March 28, 2021 by the Hon'ble Minister, Ministry of Law, Justice and Parliamentary Affairs.

- As of March 2023 total 6,434 calls have been received since the helpline was launched of which 6,410 have been resolved and rest 24 are in resolving process.

Action 7 Provide for new labour inspectors and ensure full functionality of labour inspectorate

7.1 Filling vacant posts of Labour Inspectors by recruitment and promotion

- Since the submission of the EU NAP, 95 labour inspectors have been recruited and 19 existing DIFE Officials have been promoted as Labour Inspector (Gen).

- A requisition has been sent to BPSC on 30 November 2022 for recruitment of 156 labour inspectors from 40, 44 and 45 BCS.

- Promotion of Inspector at various grades depends on finalization of gradation list (seniority list). The gradation list of Deputy Inspectors General (DIGs) has been finalized and published through gazette notification by MOLE on 6 January 2022.

- The gradation list of Assistant Inspectors General (AIGs) is currently under process of finalization on which a dedicated committee formed on 29 September 2022 is working.

7.2 Creation of new posts and recruitment of Labour Inspectors

- As of May 2022, 136 new posts of inspectors have been approved by the Finance Division. A proposal has again been sent to Finance Division on 3 December 2022 for approval of the reaming 39 posts of inspectors.

- Eight new Field Level Offices of DIFE have been establishment in 8 districts. After deployment of eight DIGs, the newly established Offices are now fully functional.

- 13 new posts for National Occupational Health and Safety Training Research Institute have been recommended by MOPA on 15 December, 2022. The issued has been referred to the Finance Division on 20 December 2022.

7.3 Full application of Labour Inspection Management Application (LIMA) digitalized labour inspection system in 23 DIFE offices

- As reported earlier, the Labour Inspection Management Application (LIMA) has been made fully operational with the support from ILO and GIZ. All the 31 district offices of DIFE are gradually using the LIMA system for inspection, licensing and other issues.

- During March 2022 to 13 March, 2023, an Admin panel Training (10 inspectors attended), a TOT (46 inspectors from 23 DIG offices attended), a Remediation Tracking Module (RTM) Training, 3 regional workshops, a Factory Facing OSH Module Workshop (77 participants from Head Office and all DIG offices attended) and 5 training courses (219 inspectors including 99 newly recruited attended) on LIMA were organized. In some cases one inspector attended two or more training counted separately.

- During July, 2021 to March 2023, a total of 25,565 inspections were carried out, 4,492 new licenses were issued and 4,131 licenses were renewed through LIMA.

- E-nothi (E-filing) system, OSH Module and complaint information by DIFE district offices have been integrated in LIMA system.

7.4 Developing competencies of Labour Inspection staff through regular trainings and capacity building measures and creating more senior positions

- Regular trainings programmes are being arrange for capacity building of labour inspectors.

- During 2022-23 FY under 12 training programmes and workshops 448 officials were trained with the help of GIZ.

- Four Foundation Training Courses have been organized for 120 labour inspectors during July 2022 to March 2023.

- For the FY 2022-23, in 22 training programmes 583 officials were trained and 178 officials attended in 6 workshops.

7.5 Promote an effective sector-specific labour inspection approach

- The prioritization of sectors for the Labour Inspectors, in consideration of safety issues and targeting establishments, was completed in December 2021.

7.6 Formulating DIFE inspection modalities for EPZs

- Modalities of DIFE inspection have been incorporated in the draft EPZ Labour Rules.

- On 30 November 2022 the Inspection Checklist has been finalized in collaboration with DIFE and accordingly the same has been shared with MoLE & DIFE.

- As of March 2023, DIFE has inspected 50 factories within EPZs.

7.7 Incorporating the Standard Operating Procedure (SOP) on Labour complaints and investigation in the BLA

- The matter is being looked into as part of BLA, 2006 amendment process.

Action 8: Ensure proper work for the Remediation Coordination Cell (RCC) and transition to Industrial Safety Unit (ISU)/Ensuring close cooperation of the RCC/ISU with the RMG Sustainability Council (RSC)

8.1 	Remediation of factories under the national initiative for fire, electrical and structural safety

8.1.1 Complete development of a business plan outlining three categories of factories including timelines for remediation

- This planning process was completed on 10 February 2021 by RCC, DIFE through categorization of the factories as:

  - Category-1: Remediation of factories easily possible by factories owner considering their technical capacity (173 factories).

  - Category-2:  Remediation of factories possible (276 factories).

  - Category-3: Remediation of factories challenging (240 factories).

8.1.2 Implement the business plan on remediation of factories

- The Remediation of Fire, Electrical and Structural safety issues is a continuous process of factories owner. To implement the business plan of category 1, DIFE has formulated a time bound Action plan to escalate the process.

- As of 1 March 2023, the Industrial Safety Unit has already visited 150 factories of category 1 for taking interim and final decision about these factories. DIFE have already issued 35 initial CAP completion certificate, and UD cancellation letter to total 10 factories. 32 Factories have already been escalated from Round-2 to Round 3. 11 Factories escalated from in Round-3 to Round 4. 44 factories are currently under second follow-up visit. Rest of the 18 factories are closed or shifted to new locations.

8.1.3 Continue to work on remediation of factories under category 2 and 3, including with support from relevant international development partners

- This is a long-Term target as the factories are very weak terms of financial resources, located in rented building, very small and subcontract factories.

- A new Project named “Risk Assessment and Remediation Implementation in selected factories to reduce accidents” was initiated to cover factories under category 2 and category 3.

- Due to on-going finical crisis, instead of the project, a specific proposal has been shared with ILO for their assistance.

8.2	Enhancing quality control and transparency of the RCC

8.2.1	Develop a quality assessment mechanism for remediation being monitored by RCC and apply it.

- This step has been accomplished.

8.2.2 Ensure full application of Remediation Tracking Module (RTM)

- Technical Work is completed and factories under category 1, have been uploaded in the tracking module.

8.3 Establishing a transition plan to graduate RCC to ISU

8.3.1 Upon project completion, RCC to handover the remediation work to DIFE Safety Unit

- This action was completed in December 2021.

    - Post Creation and Deployment of Labour Inspectors for the ISU

- In the up-gradation proposal of DIFE 92 posts for ISU in 8 divissional offices with 80 dedicated engineers. The current fiscal constraints aggravated since the outbreak of the Ukraine war, poses practical challenges for such reconsideration.

- However, alternatively DIFE already formed an ISU in head quarter on 21 March 2022 with the support of ILO. Presently 12 Engineers of DIFE, 9 ILO supported Engineers and 2 Data management officer are working in ISU.

8.3.3	Upon establishment of ISU, DIFE Safety Unit to handover the responsibility to ISU

- Please refer to Action 8.3.2.

    - Capacity building and training of DIFE’s existing Engineers on building safety (fire, structure, electrical, chemical, boilers etc.)

- Apart from Covid-19 pandemic situation, the capacity building training sessions for the DIFE safety unit’s 47 engineers have been conducted in November, 2021 and June 2022. The engineers also availed special Master Training in Structural, Fire and Electrical Safety Issues with the help of ILO.

8.4  Development of a framework for coordination with RMG Sustainability Council (RSC)

- The RSC was officially registered by the Office of the Registrar of Joint Stock Companies and Firms, Bangladesh on 20 May 2020.

- To ensure effective coordination with DIFE and RSC, a Government Coordination Council (GCC) has been formed under the Ministry of Commerce.

- A Framework for coordination with the RSC has been approved GCC on 20 October, 2022.

- A 10-member Review Panel for RSC has been formed.

- Since 23 December 2021 four meetings of GCC have been organized including the last one held on 21st December 2022.

- The representatives of RSC are also attending the GCC meeting.

Action 9 Ratify ILO Convention on minimum age and Forced Labour Protocol

9.1 Ratify Protocol of 2014 to ILO Convention on forced labour (P29)

- Bangladesh has ratified protocol of ILO Convention 29 on 20 January 2022. It has entered into force for Bangladesh on 20 January 2023.

9.2 Ratify ILO Convention 138 on minimum age (C138)

- Bangladesh has ratified the ILO Minimum Age Convention 138 on 22 March 2022 and has set the minimum age of 14 for admission to employment.

- With this, Bangladesh has reached the milestone of ratifying eight ILO Fundamental Conventions of ILO.

***